WORK ORDER/ AGREEMENT

To,                                                                                                                               DATE-09/07/2025

Kamal Constructions

SR No- 12/2/2/1 to 5,3rd Floor, Building No-E-4

Gaikwad Galaxy Commercial, Fortune P,

Somaji  Chowk, Kondawa Pune- 411048

PAN NO- ABDFK2887R

Kind attention – Mr. Nilesh Patel.

Subject: - Work Order for Civil Work at site CTS 400,401,402A,402B,404. Nana Peth Pune -411002.

Ref.: Your offer Dated - 10th June 2025.

Dear Sir,

We are pleased to mention herewith that the Civil work of proposed Tower at our project               B.T. Square, Nana Peth Pune 411002.  is awarded to you based on following

Terms and conditions.

Work order value after agreed discount works out to Approximate Rs. 27,90,43,605/- (In Word –Twenty  Seven Crore Ninety Lac Forty Three Thousand Six Hundred & Five Only. This price is exclusive of all taxes and duties.

You shall carry out entire works at Rs. 985 per sqft. Based on various drawings, specifications, instruction issued by the client from time to time. Your work is based on Labour with Materials. Item Rates are defined in Annexure C. Your rates will remain firm without any escalation for entire period of project.

Item rates described in Annexure C

Annexure C.

ITEM RATE

| SR NO | DESCRIPTION | UNIT | FINAL RATE | REMARK |
| --- | --- | --- | --- | --- |
| 1 | BASEMENT RAFT 350mm THK excluding footing are | Sq.ft. | 450.00 |  |
| 2 | RETAING WALL FOR ALL HEIGHT | Sq.ft. | 550.00 |  |
| 3 | PLUM CONCRETE | CUM | 4000.00 |  |
| 4 | UGWT | LTR | 18.00 |  |

Constant for consumption of material –

- Reinforcement 5.50 kg per sq.ft. On total built up area. (2% quantity + or – to be considered in final billing without raft & retaining wall, UGWT)

- Concrete 1.25 cu.ft. Per sq.ft Total built up area. (2% quantity + or – to be considered in final billing excluding raft & retaining wall, UGWT)

- Scope of Work:

The contract will be Labour with Materials with installation of TOWER CRANE. The scope of work will include all the materials, labour, supervision, tools/tackles, machineries, safety, Quality testing of materials etc. required for administering and executing all works complete in all respects as per GFC drawings and technical specifications.

You will carry out various items as mentioned/set out in tender document, more specifically in following order in addition to this, if required you will carry out non-tender work and / or miscellaneous work as per instructions of Owner’s, Project Head/Construction based on derived from item rates defined in BOQ. For items

You have get prior approval for which item not mentioned in BOQ from Owner, Project Head.

You shall carry out civil work consisting of following work package for RCC Work.

- Reinforce concrete of various grades of concrete as per structural design for foundation, plinth stub columns, plinth beams, columns, beams, slabs, staircase along with various elevation treatment. (THE COLUMNS SHOULD BE CAST ONE GRADE ABOVE AS DESIGN GIVEN BY RCC CONSULTANT), Hacking of all exposed concrete to receive plaster (if Hacking not possible then you have to apply bond It or Hack Aid plast chemical your own cost & as per procedure of manufacturer.

- Shuttering for all concrete elements. (The shuttering material coming in contact with concrete shall be made out of New Plywood and supports shall be MS props & Spans) During course of execution any worn off or bad quality material to be replaced immediately. You have to apply fresh oil to ply, as the surface of concrete product will clean

- Reinforcement has to use grade reinforcement steel which will specified by RCC consultant, With M.S. Binding wire and precast FRC concrete cover blocks of approved make

- work including lintel/boxing, elevation features, parapet walls to parking area & top terrace as mentioned in drawing etc. complete

- Mode of Measurement:

Mode of Measurement of works will be as mentioned in the contract document. Wherever not specified in the contract document, IS 1200 published by Bureau of Indian standards (BIS) will be referred.

- Out to out slab will be measured,

- Basic height of slab considered 4.2m for  basement parking’s, 5.40m for Upper Ground floor of commercial with mezzanine & 3.30m for residential, commercial in super structure above this height no extra multiplication for height rise considered due to L+M contract, only the materiel cost required for extra concrete & steel will paid for this activity. No labour charges given extra.

- Duct more than 10 sqft will be deduct in area calculation.

- No elevation & projection will have measured as extra cost.

- Double chajja projections measured on time, bottom chajja will not measure for area calculations. Only top chajja will measured.

- Raft area will have measured after deduction of footing area & lift raft area.

- UGWT considered on LTR basis, so measurement of UGWT raft, surroundings & inside RT walls & top slab not taken in area calculations. Pump room of UGWT will not paid on LTR basis, normal measurements will applicable as raft, RT wall & top slab paid against built up area basis.

- Foundation PCC & plinth PCC not paid extra.

- Plinth PCC of THK 100 will deducted from plum concrete measurement.

- RT wall measured from top of Raft & up to slab beam bottom.

- Entire Service slab of toilets ducts & services not measured in built up area.

- RCC parapet wall all over building included in built up area rates, not paid extra item.

- Lift duct will not have deducted in area calculation.

- Car lift & two-wheeler lift area will measure as plan area, no extra charges for RCC walls & height staging.

- Staircase area will measure in plan.

- Chajjas, lintels, sills, bunds, and elevation projections shall not measure for payments, if contractor fails for that then double debit arranged to actual cost by Owner.

- No plinth area will have measured for payment.

- OHWT will measure top & bottom slab area, it will not give on LTR basis.

- The measurement for Retaining walls not considered for Car lift & Two-wheeler lift as this item taken in sq.ft. Basis in L + M contract.

- Scope of work & terms, Technical specification.

- The scope of work includes supplying, making, erecting, dismantling of form work & staging, Labor concreting Mixing, transporting, Placing, Finishing, Hacking & labor for receiving reinforcement steel, straitening, cutting, binding, transporting, placing position, binding making & fixing of concrete cover etc. complete as per GFC drawing, details & instruction of project manager or his representative.

Following activities are included in the agreed rate for required labor, machineries, formwork materiel, small tool, tackles etc.

- Entire RCC work in sub structure & super structure including plinth, Retaining walls, Raft, UGWT.

- Surveying of all column centerline marking, retaining walls marking at your scope.

- Mathadi chargers for loading & unloading of all materiel required for RCC in your scope.

- All other formwork, concrete and reinforcement work shown on drawing or as instructed by Project Manager

- Hacking of all RCC works wherever plastering is required 50 no’s per sq.ft.or applying Hack aid/ Bond It Adhesive.

- You have to submit quality, quantity, recon solation report with each of billing.

- Every incoming materiel bills, invoice, challans have to submit prior to unloading of materiel or before consumption of materiel.

- All planks, ply boards/ steel centering plates shall be applied with de-shuttering oil, as approved by” the engineer, before reinforcement. Not use the black oil or waste motor oil.

- Binding wire for holding the form work / centering in position shall be purchased by the labor contractor at his cost

- The tie rod holes (if any), shall be filled with non - shrink grout. You will supply grouting material at your own cost.

- Casting of minimum 12 cubes for each major concreting and shifting the cubes from the place of concreting to the “curing tank.

- The testing of Cube & steel per lot with approved testing agency by your responsibility with your cost, maintain the record also your responsibility.

- The contractor shall provide and place sleeves, pockets, inserts etc., in.RCC for plumbing, electrical, firefighting, lift Ac, etc.

- The contractor shall adequately and sufficiently cure all R.C.C work. The tools and materials for the curing like pumps, curing line, curing pipes, buckets, drums, Hessian cloths shall be brought by the contractor to Curing of slab shall be done by ponding method by making ponds in cement mortar of size around 5’0” x 5’0”.

- Curing for columns shall be done by hessian cloth at your cost.

- The starter should be cast in Grid wise of min 150 mm high with proper compaction by needle vibrator.

- The contractor has to mark the date/ no’s of casting for particular columns & slab by paint in proper finish & font.

- The contractor shall coordinate with plumbing & electrical contractors for their work during in progress of RCC work.

- The contractor has given proper finish to all RCC surface by removing dirt, duct & clean proper finish by grinding.

- Plant & Machinery

- Contractor should be having 2 electrical vibrators with 1 diesel vibrator in spare & 40mm, 60mm needle in spare.

- The curing pump with curing pipe for entire RCC work.

- Tower crane with authorized operator for each shift.

- Grinding machine

- Breaker tools

- Bar bending & cutting machine.

- Fabrication welding machine.

- Contractor should be having adequate form work to achieve the schedule& no excused shall be accepted for delay due to inadequate shuttering.

- Price of Contract

Based on final discussions you have agreed for price of Approximate Rs. 27,90,43,605/-  (In Word –Twenty Seven Crore Ninety Lac Forty Three Thousand Six Hundred & Five Only which excludes all taxes and duties as detailed in Annexure C.

- Basic Rates of Material

Since this contract is based on Basic rate of material, you will take Clients approval on Make/Quantity/Rate every time you do a purchase of material. You will carry out this process once a month along with nominated person from Client side. You shall maintain all records of material purchase/ site receipt, etc. in a register, which will form the basis for basic rate variation working. Client will review basic variation of material and actual credit or debit will be passed with every RA bill.

Basic rates will effectively applicable after rise & decrease in rates by plus or minus 5%.

Annexure B.

### BASIC RATES OF MATERIALS

| Sr. No. | Description of Material | Unft | Basic Rate | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Cement ( Vasavdatta, Birla53 G, jk) | Bag | 250.00 |  |
| 2 | Crush Sand | brass | 3500.00 |  |
| 3 | Plaster sand | Cum | 6200.00 |  |
| 4 | 10 – 20mm Metal | brass | 3200.00 |  |
|  | RMC( ACC, Prism Johnson, Ultratech) |  |  |  |
| 5 | M15 | Cum | 3772.00 |  |
| 6 | M20 | Cum | 4100.00 |  |
| 7 | M25 | Cum | 4223.00 |  |
| 8 | M30 | Cum | 4428.00 |  |
| 9 | M40 | Cum | 4776.50 |  |
| 10 | M45 | Cu.m. | 5170.00 |  |
| 10 | Reinforcement Steel | MT | 55000.00 |  |
| 11 | Binding wire | kg | 68.00 |  |

  - Materials Supplied by Owner:

There shall not be any material supplied to you by owners.

  - Taxes & Duties:

### The contract price is exclusive of all taxes GST and all duties as per statutory requirements. TDS and works contracts tax as applicable will be deducted from your bills. In the eventuality of any increase/decrease in the prevailing taxes imposed by the state or central government, during the currency of the contract, the same shall be paid to you/reimbursed to us (in case of decrease) on submission of supporting documents in support of claim.

- Time of Completion:

| ITEM - | Duration (Working Days) |
| --- | --- |
| RCC up to Ground level1st Slab | 90 |
| RCC 1st to 25th Slab, | 405 |
| LMR, Staircase Top, Water Tank etc. | 45 |

In case of delays caused due to the reasons beyond control of contractor like force majeure, transportation strikes etc. the same to be considered and suitable time extension shall be granted to contractor.

Also any delay caused due to delay in drawings to be issued or material to be supplied by clients, the same can be considered for suitable time extension.

Any such time extensions sought by contractor are to be brought to the notice of owners at each intermediate milestone for approval.

- Defects Liability Period:

You have offered 12 months’ period for Defects Liability (starting from the date of virtual completion certification). During defects, you free of cost shall do liability period if any repairs/rectification needs to be carried out the same forthwith. In case you do not do the job in the given timelines, the work will be carried out by the owner at the your 'Risk and cost'.

- Liquidated Damages:

In case work is delayed beyond 12 months (and approved time extensions), a penalty of 0.5% of contract value per fortnight maximum up to 5% of contract value will be levied. During the project's lifespan, progress will be monitored against baseline plan & key milestone and payment will be linked to adherence of key milestones

- Land for Labor Camp etc.

Land for labour camp, office, stores etc. will be provided at site free of cost as and when

it is available at site. In Special case at some sites labour camp land will not available in

that contract the contractor should arrange at its own cost and amount to be considered

separately before sign the contract

You shall do shifting of labour hutments during the work progress with no liability/extra cost. The decision of our Owner's Project Head/Construction Head regarding this will be final. You will be responsible for your labour management and upon completion of work; you will remove the labour camp etc. outside of the site. You will maintain the cleanliness and hygienic condition of the entire site including the labour to the full satisfaction of the Construction Head.

- Weekly/Fortnightly Meeting:

Weekly/ Fortnightly co-ordination and progress monitoring meetings will be held at site.

All concerned, site as well as your Head office staff shall attend the meeting.

- Weekly progress meeting with your site staff.

- Fourh nightly review meeting with your subcontractor & principal contractor.

- Monthly meeting with client, principal contractor & sub-contractor.

- Drawings for Construction:

Drawings for construction will be issued progressively to meet the schedule. You will intimate Engineer in charge/Owner well in advance the requirement for drawings so that the progress of work is not hampered. Owner shall issue 03 sets (Three sets) of hard copy for each "GFC" drawing. Additional drawings copies will be given to you on chargeable basis.

- Insurance: As per Annexure TF

- The contractor shall comply wit following act or any other labour law.

- Employees state insurance act

- Provided fund act

- The minimum wages act

- The payment of wages act

- Contract labour ( Regulation & Abolition ) Act 1970

- Tower crane stability certificate from third party.

- Labour Laws:

You will comply with all labour laws and submit statutory information to various government authorities. Proper work condition and Labour Camp conditions will be made available to labours working on this project. You will ensure all medical facilities, regular checkup, crèche for children's of labours are arranged free of cost.

- You should submit all labours AADHAR CARD for identification & submit report every fortnightly to client office.

- No child labour allowed to work & or in premises of construction area.

- Keeping labour camp hygiene condition in your scope by cleaning, garbage cleaning, toilets bath cleaning, spraying for mosquito control.

- You should arrange potable drinking water &usable water to labours at your own risk.

- SAFETY COMPLIENCE-

The Contractor shall ensure that all their staff and workers including their sub­ contractor(s)'s have been issued & wear appropriate PPE's like safety helmets, safety shoes, full body harness, reflective jacket, protective goggles, gloves etc. All these gadgets shall confirm to applicable IS Specifications/CE or other applicable international standards. In case of non-compliance or repeated failure in implementation of PPE policy impose INR 1000/­ per incident as penalty. Contractor shall arrange (at his cost) and ensure use of Fall Arrester Systems by his workers. Fall arresters are to be used while climbing tall structures. These arresters should lock automatically against the anchorage line, restricting free fall of the user. Contractor shall ensure that a proper Safety Net System is used wherever the hazard of fall from height is present. The safety net shall be located not more than 6.0 meters below the working surface extending on either side up to sufficient margin to arrest or to reduce the consequences of a possible fall of persons working at different heights.

- Its contractor’s responsibility to maintain the site & the structure totally clean, stack all material neatly, observe all safety precautions.

- The contractor shall follow the guidelines & instruction given by project head/ safety officer appointed by client at all the time & keep the safety working environment at site at all the time.

- The contractor shall indemnify the client against the all-risk, cost & legal obligation in case of any accident to concoctors laborer. The contractors shall liaise with local authority, police & other such as authorities & keep indemnified at all the time against any obligation due the accident.

- Provision for lift shaft protection- masonry or fabrication grill work up to 1.2 m to be incorporated in the contract, detail sketch to be provided by contractor.

- Edge protection; binding of steel bars at slab levels, edges to be part of RCC contractors, edge protection scheme to be submitted by main contractor same to be reviewed.

- Debris- waste chute provision including cleaning of debris at least one waste should to be provided every stage, the debris should be removed from construction site is a responsibility of contractor.

- Danger sign & posters to be displayed at site & site premises.

- Daily Induction – for better understanding, awareness & review of safety practice followed.

- Tool box Talks – Every Days, report to be submit on weekly basis to client.

- Work permit- work permit to be arranged on daily basis from client to start the specific work.

- You should provide safe access to client, engineering staff & to your labors.

- SAFETY NETS-

- Safety nets shall be installed as close as practicable under the walking/ working surface on which employees are working & never more than 30 feet below such levels. Defective nets shall not be used.

- Safety net shall be inspected at least once a week for wear, damage & other deterioration.

- All ducts, dangerous openings should be closed by safety net.

- as per new rule by PMC top 2 floors of building should be cover by green net is responsibly of contractors.

- SAFETY TRAINING-

- Working site safety procedure.

- Employer & employee responsibilities.

- Electrical safety

- First aid & medical facilities & emergency procedure.

- Safety harness & life line

- House keeping

- Working at height

- Accident & near miss reporting.

- FIRST AID

- You should provide first aid box on site for emergency as per guidelines of safety officer or site in charge.

- PENALTY CLAUSES.

| SR NO | TYPES OF NON CONFORMITY | PENALTY FOR EACH LAPSE |
| --- | --- | --- |
| 1 | Not Wearing Personal Protection Equipment ( PPE ) | RS- 100/- |
| 2 | Not Wearing Safety Belts | RS- 500/- |
| 3 | Damage Of Safety Nets | RS- 1000/- |
| 4 | Barricading Of staircase ,Lift shaft ,Ducts ,Opening In slabs | RS- 500/- |
| 5 | Presence of child labours in working condition Or site premises | RS- 500/- |

The contractor shall maintain/ submit HSE records in the following reporting formats:

  - Monthly HSE Checklist cum compliance report

  - Accident/ Fire Report, Near Miss Report.

  - Supplementary Accident & Investigation report

  - Monthly HSE Report

  - Work permit records

  - Tool box meeting report

### Safety Audit

The Company shall, at its own discretion, conduct safety audit of the ongoing Work using either its own resources or by engaging a third-Party Consultant. The Contractor shall have a track of all safety records including hazard identification, risk assessment and risk control, legal compliance and other requirements as described in Company's Contract Safety Rules and regulations and incorporated

in the approved Project Safety Plan and other relevant documents as required

The Contractor Shall cooperate with the Company or the third-Party Safety auditors for conducting such a Safety audit in all respects including but not limited to making available all the relevant records, notes, findings etc. In addition, the Contractor shall take the recommended action to implement the findings of Safety audit.

The Contractor shall maintain minimum scoring as instructed by the Company.

- Contractor’s Manpower: -

You will maintain minimum qualified technical staff for smooth progress of work.

Following Minimum staff is required to be deployed for the project

- Project Engineer (8-10 Years’ Experience)

- Site Engineer - Concrete/ Reinforcement/ Shuttering

- Sr. Site supervisor

- Sr. Quality Engineer

- Sr. Safety Officer (for Site & Labor Camp)

- Store Keeper

- Site Billing Engineer & Site Planning Engineer

- Contractor’s minimum Staff & Labour Requirement details per Day per Building

- Competent, Crane OP, Qualified full time Engineer -1, Supervisor-1, Safety Engg-1

- Carpenter with Helper :35+ (Basement floor)

- Fitter with Helper          :25+ (Basement floor)

- Labor for Concreting :15+(Basement floor )

- Department Labor      : As per Need and will be informed in Advance

- Labor for Couplers threading work    : 2 nos.

- Labor for Rock anchoring work: As per requirement

- You will also maintain adequate strength of labors (Skilled & Unskilled) to complete the work in scheduled time. Any negative side deviation to deployment of technical staff at site will not be accepted and if required Owner will get the required strength as mentioned in minimum OS requirement at your risks & costs.

- Working Time:

The working time at site shall be from 9.00 am to 10.00 pm, Monday to Saturday except public holidays. You will be permitted to work around the clock provided there are no objections from neighborhood or authorities. You will intimate us in advance for works to be carried out on Sundays and Holidays.

In case of work executed needs to be carried out beyond permitted time, the same shall be at your own risks and costs; and no extra claim for cost increase will be entertained. No time extension request, due to work not getting completed in normal working time, will be entertained while settling Liquidated damages.

- Water for Construction:

Company will provide enough clean and potable water for the construction purpose. No turbid water shall be used on the work. The decision of Owner shall be final in this regard.

The water proposed to be used should be tested by you at your own cost.

You shall maintain adequate storage of water at all times to ensure continuous work without stoppage for want of water.

You will be allowed to construct bore wells (obtaining necessary permissions from local Authority) on your own, within the Project site for getting water, after written consent from the Owner's Project Head/Construction Head. You will, at your cost, make necessary arrangements to provide temporary service lines and to avoid any accident or damage to the buildings, roads, and service lines adjacent to the bore wells sunk. The cost of bore well and pumps shall be reimbursed to you after the execution of work and upon submission of invoice with supporting documents. You will maintain the bore well in proper working condition till the completion of the project.

- Electric Supply for Construction:

Company shall be provided electric supply at one point within the site on chargeable basis. Further, you will make your own arrangement for the distribution of the same for entire project work. All the works shall be done as per Indian Electricity rules.

A separate sub meter shall be installed by you and an amount of Monthly Bills/ charges against the power consumed by you for your machinery, lighting, labour, camp etc. will be debited from your bills.

The temporary lines/structures shall be removed by you at your own cost after completion of the work as directed. If there is any hindrance to the other works due to these lines/structures during the progress of work the same shall be realigned at your cost.

You will be responsible to make adequate infrastructure and standby facilities for the continuous supply of electric power required for the satisfactory execution of the work without stoppage.

You should arrange DG back up for construction purpose for your machineries in case of electricity failure.

- Incidental Expenses:

All incidental expenses towards local police, traffic or any other authorities etc. for successfully carrying out your scope of the work are included in your contract amount.

- Form Work:

All RCC formwork for Conventional work shall be with Film coated plywood and wall form for columns as required for the work.

- Reinforced Concrete:

PVC sleeves material will be provided by company and labour for fixing of sleeves will be provided by us. That to only for building related RCC work.

- HSE:

You will follow all HSE norms in letter & sprit. You will maintain acceptable hygiene conditions at site as well as at labour camp, comply with all statutory health regulation & requirements. You will follow all safety rules & regulation at site & in labour camp.

- Settlement of Disputes:

  - Matter to be settled by Owner:

All disputes and differences of any kind whatsoever arising out of or in connection with the contract, whether during the progress of the works or after their completion shall be referred by YOU to the OWNER and the OWNER shall within a reasonable time after their presentation make and notify decisions thereon in writing.

The decisions, directions, clarifications, measurements, drawings and certificates with respect to any matter the decision for which is specifically provided for by these or other special conditions to be given and made by the OWNER are matters which are referred to hereinafter as excepted matters and shall be final and binding upon YOU and shall not be set aside on account of non-observance of any formality, any omission, delay or error in proceeding in or about the same or on any other ground or for any reason and shall be without Appeal.

Every dispute, difference, or question which may at any time arise between the parties hereto or any person claiming under them, touching or arising out of or in respect of this agreement (deed) or the subject matter thereof shall be referred to two arbitrators one to be appointed by each party to the difference (whether consisting of one or more than one person) and in case of difference of opinion between them to an umpire appointed by the said two arbitrators before entering on the reference and the decision of the arbitrator (or such arbitrators, or umpire as the case may be) shall be final and binding on the parties. The venue of such Arbitration shall be Pune.

The award of the arbitrator shall be final and binding upon the parties and will be

entered and/or enforced in the court of Pune jurisdiction.

Notwithstanding any other rights of the OWNER, OWNER may seek injunctive relief in any      court of competent jurisdiction against improper use or disclosure of any confidential    information of the OWNER. As used herein Confidential Information shall mean all information of the OWNER disclosed to you at any time from the date of receipt of the Tender documents by

you from the OWNER or its PROJECT MANAGER relating to any matter the subject of the Tender and Contract.

- Risk Purchase Clause:

If the material supplied is not as per the order specifications or fails to perform specified duties, or the work carried out by you/job executed by you does not meet the entire satisfaction of Owner/Owner's consultant, Owner shall have the right to reject the material or work completed or job executed either in full or in part and seek replacement of material & rework by you. If the free replacement is not provided or rework / job not carried out within a reasonable period of time as specified by Owner, Owner will have the right to procure the material & get the job done from any other source of Owner's choice, at your entire cost & risk. Further, if the progress of execution of the order is not to the satisfaction of Owner, then Owner, after serving a notice, shall be free to revoke the Risk Purchase Clause as stated above. Owner also reserves the right to recover the additional cost of procurement or additional job done from other source from your pending invoices or by other means as per its own discretion.

- Termination:

In case of non-performance by you as determined by Owner, this contract can be terminated by Owner after giving due notice to you and no compensation will be payable by Owner. All the completed work or incomplete work/materials/design & all documents which form part of the contract and the tender document upon termination will be the sole property of Owner

- Documents of contract:

This order to the extent modified herein shall supersede any condition mentioned in the attached documents or correspondence between us and shall form a binding contract between us.

The points mentioned in this work order letter shall supersede any condition mentioned in our Tender document/ various correspondences between us.

The Company shall, at its own discretion, conduct Quality audit of the ongoing Work using either its own resources or by engaging a third-Party Consultant. The Contractor shall have a track of all Quality records including Approved Quality Management Plan and other relevant documents as required.

The Contractor shall cooperate with the Company or the third-Party quality auditors for conducting such a Quality audit in all respects including but not limited to making available all the relevant records, notes, findings etc. In addition, the Contractor shall take the recommended action to implement the findings of Quality Audit.

- Inspection, Quality, Surveillance, Rejection of Materiel, Workman ship & penalties for Quality:

- The contractor has to be appoint Qualified engineering staff with quality Engineer,

- The owner or His subordinate engineer having rights to accept or reject the materiel as per IS 456.

- The owner or His subordinate engineer having rights to accept or reject post construction product or object.

- If the quality testing report being failed then NDT will be done, contractor at his own cost shall do If NDT test report also got fail then the whole member strengthen as per guide lines given by RCC consultant.

| SR NO | TYPES OF NON CONFORMITY | PENALTY FOR EACH LAPSE |
| --- | --- | --- |
| 1 | Honey combing of columns & other elements. | Rs 5000/- |
| 2 | Buldging of columns, beams & other elements | RS- 5000/- |
| 3 | Out of plumb or line within IS limit | RS- 5000/- |
| 4 | Undulations in slab soffit or beams line | RS- 10000/- |

## ANNEXURE A - APPENDIX TF

Following items are list of terms & condition agreed between Owner & contractor and supersedes any other reference to the said term in any document which forms part of tender/work order.

SUMMARY OF NOTICE INVITING TENDER AND CONTRACT CONDITIONS

1. Insurance                                                                  :  All Risk (CAR)

Third Party liability

Workmen's compensation

2)      Liquidated damages

a) Amount                                                              : 5% of contract price after 12 months

3)     Limit of variation                                                        : No Limit

4)    Period of defects liability                                            : One calendar year from date of virtual

Completion certification

5)    Escalation                                                                   Not applicable. Prices to remain firm

during the contract period and also  extended

contract period

6)   Period of interim certificate                                                 :  Monthly

7) Payment of Bills Certificate                                                   : a) 15 days from the submission of

Bill with all other supporting documents

8) Rate of Interest for delayed payment                                     : Nil

9) Type Of Contract                                                                    :   with Material and labour contract.

10) Earnest Money                                                                      :   NIL.

11) Material basic rate                                                                  :  Please refer basic rate schedule

Accepted with all terms & conditions

For, Shreeyash Infra Realty Pvt Ltd.                                                                        Kamal Constructions

Authorize Signatory	                                                                                         Authorized Signatory

### MATERIAL WITH BASIC RATE

In this tender there is no free supply of material. All material should be brought in by civil contractor at his risks and costs as per details and specifications described in tender document for all "A CLASS" materials. Basic rate of materials is given in the BOU to avoid discrepancy and parity in quote. Contractor is requested to follow these basic rates along with material consumption content given in the BOQ. Basic rate of material will be landed cost of material at site including all taxes, duties, transportation, loading, insurance during transit cost. This cost does not include cost of unloading, storage at site, which has to be managed by successful bidder at his own risk and cost.

In case for some reason if contractor is not able to procure material at basic rate, client reserves to choose between one of the following option available at his discretion between following options:

For, Shreeyash Infra Realty Pvt   Ltd.                                                           Kamal Constructions

Authorized Signatory                                                                       Authorized Signatory

PAYMENT STAGE

| TOTAL AREA IN SQFT | 283293 SQFT |
| --- | --- |
| RATE IN SQFT | 985 PER SQFT |
| TOTAL AMT- | 27,90,43,605/- |

| SR NO | STAGES | AREA | RATE | RETENTION 5% | AMOUNT |
| --- | --- | --- | --- | --- | --- |